## Schedule
CCNA-12 ¦ Secure Campus Segmentation and Access Control for FIDS ¦ Schedule and Time Management
Project Manager: Carl Edouard Sponsor: Fairmont Integrated Defense Solutions Built on the eight week WBS in Appendix B of the signed scope, tracked in Jira as five sprints
Start |  | Baseline finish (signed scope) |  | Forecast finish |  | Course deadline |  | Total duration (days) |  | Buffer left before deadline (days) |  | Tasks complete
2026-09-29 |  | 2026-11-21 |  | 2026-12-01 |  | 2026-12-05 |  | 64 |  | 3 |  | 10 of 40
[12 empty] | SEP |  | OCT | [30 empty] | NOV | [29 empty] | DEC
WBS | Activity | Owner | Start | Finish | Days | Depends on | Status | Type | Baseline start | Baseline finish | Slip (days) | time axis 2026-09-29 to 2026-12-05
S1 | SPRINT 1 (Jira) | All | 2026-09-29 | 2026-10-10 | 12 |  | Complete | Sprint
W1 | WEEK 1 Understand the job and lay the foundation | All | 2026-09-29 | 2026-10-03 | 5 |  | Complete | Week | 2026-09-29 | 2026-10-03 | 0
1.1 | Read the scope, list every requirement, and log questions for the sponsor | Carl | 2026-09-29 | 2026-09-30 | 2 |  | Complete | Task
1.2 | Study the core skills in NetAcad: VLANs, OSPF routing and ACL rules (SRWE 3 and 4, ENSA 1 to 4) | All | 2026-09-29 | 2026-10-03 | 5 |  | Complete | Task
1.3 | Draw the physical layout: where each router and switch sits, which zone joins which OSPF area, how it is all cabled | Devam | 2026-09-30 | 2026-10-02 | 3 | 1.1 | Complete | Task
1.4 | Agree on one naming system for devices and port descriptions so every config reads the same way | Carl, Devam | 2026-10-01 | 2026-10-02 | 2 | 1.3 | Complete | Task
1.5 | Create the GitHub repository; all four members commit the starting topology | Carl | 2026-09-30 | 2026-10-03 | 4 |  | Complete | Task
1.6 | Set up the Jira board with five sprints to track the work | Carl | 2026-10-01 | 2026-10-03 | 3 |  | Complete | Task
G1 | GATE Layout and naming agreed by all four, everyone committing to GitHub | Carl | 2026-10-03 | 2026-10-03 | 1 | 1.3, 1.4, 1.5 | Complete | Gate
W2 | WEEK 2 Plan every address and every rule on paper before touching a device | Jaden, Carl | 2026-10-06 | 2026-10-17 | 12 | G1 | In progress | Week | 2026-10-06 | 2026-10-10 | 7
2.1 | Addressing plan (VLSM): size each zone's IP range so the whole zone can be advertised as one summary route at its border router | Jaden | 2026-10-06 | 2026-10-13 | 8 | G1 | Complete | Task
2.2 | Map each VLAN to its OSPF area and write down why | Jaden, Carl | 2026-10-07 | 2026-10-13 | 7 | 2.1 | Complete | Task
2.3 | Policy matrix: for every pair of zones, in each direction, decide allow or block and record the reason | Jaden, Michael | 2026-10-08 | 2026-10-13 | 6 | 2.1 | Complete | Task
2.4 | Give each router a fixed router ID and map the path traffic should take between zones | Carl | 2026-10-08 | 2026-10-13 | 6 | 2.2 | Complete | Task
2.5 | Sponsor acknowledges the scope on Discord | Carl | 2026-10-08 | 2026-10-08 | 1 |  | Complete | Gate
2.6 | PM Readiness Package submitted on Canvas | Carl | 2026-10-13 | 2026-10-13 | 1 | 2.5 | Complete | Gate
2.7 | PM approves the addressing plan, then sends the plan and matrix to Thompson | Carl | 2026-10-15 | 2026-10-15 | 1 | 2.1, 2.3, 2.5 | Not started | Task
G2 | GATE SPONSOR DESIGN REVIEW: Thompson approves the plan and matrix. Nothing is configured before this. | Carl | 2026-10-17 | 2026-10-17 | 1 | 2.7 | Replanned | Gate
S2 | SPRINT 2 (Jira) | All | 2026-10-13 | 2026-10-24 | 12 | G1 | In progress | Sprint
W3 | WEEK 3 Build the backbone and the zones, with no blocking yet | All | 2026-10-13 | 2026-10-24 | 12 | 2.4 | In progress | Week | 2026-10-13 | 2026-10-17 | 7
3.0 | Prep during the review: place and cable every device in Packet Tracer, write each config as a text file ready to paste | All | 2026-10-13 | 2026-10-17 | 5 | 2.4 | In progress | Task
3.1 | Bring up the management backbone and OSPF routing across all areas, using the fixed router IDs | Carl | 2026-10-20 | 2026-10-22 | 3 | G2, 3.0 | Not started | Task
3.2 | Create each zone's VLANs, link switches with 802.1Q trunks, and turn on routing between VLANs | Jaden, Michael, Devam | 2026-10-20 | 2026-10-23 | 4 | G2, 3.0 | Not started | Task
3.3 | Ping test inside every zone and save proof that the routers became OSPF neighbors | Michael | 2026-10-22 | 2026-10-23 | 2 | 3.1, 3.2 | Not started | Task
3.4 | Confirm each border router advertises its zone as one summary route, matching the Week 2 plan | Jaden | 2026-10-23 | 2026-10-23 | 1 | 3.1 | Not started | Task
3.5 | Save a before snapshot of traffic so the effect of the ACLs can be shown later | Devam | 2026-10-23 | 2026-10-24 | 2 | 3.3 | Not started | Task
G3 | GATE All OSPF neighbors FULL, every zone reaches itself, summary routes visible, no ACLs yet | Carl | 2026-10-24 | 2026-10-24 | 1 | 3.3, 3.4, 3.5 | Not started | Gate
S3 | SPRINT 3 (Jira) | All | 2026-10-27 | 2026-11-07 | 12 | G3 | Not started | Sprint
W4 | WEEK 4 Turn on the rules between zones (ACLs) | Jaden | 2026-10-27 | 2026-10-31 | 5 | G3 | Not started | Week | 2026-10-20 | 2026-10-24 | 7
4.1 | Write extended ACLs for every zone border, check each line against the matrix, then apply them | Jaden | 2026-10-27 | 2026-10-29 | 3 | G3 | Not started | Task
4.2 | DMZ rules by service: allow only the named services on each server, block every other port | Devam, Jaden | 2026-10-28 | 2026-10-30 | 3 | 4.1 | Not started | Task
4.3 | Test allowed traffic first, then confirm blocked traffic is actually blocked | Michael | 2026-10-29 | 2026-10-30 | 2 | 4.1 | Not started | Task
4.4 | Capture ACL hit counters before and after each test; confirm Contractor/Guest reaches nothing internal | Michael | 2026-10-30 | 2026-10-31 | 2 | 4.3 | Not started | Task
G4 | GATE Every rule does what the matrix says, and hit counters prove it | Jaden | 2026-10-31 | 2026-10-31 | 1 | 4.2, 4.4 | Not started | Gate
W5 | WEEK 5 Test every zone pair and train on each other's zones | Michael | 2026-11-03 | 2026-11-07 | 5 | G4 | Not started | Week | 2026-10-27 | 2026-10-31 | 7
5.1 | Test every pair of zones in both directions and save proof for each one | Michael, All | 2026-11-03 | 2026-11-05 | 3 | G4 | Not started | Task
5.2 | Turn on logging for key block rules and capture a blocked attempt as it happens | Michael | 2026-11-04 | 2026-11-05 | 2 | G4 | Not started | Task
5.3 | Fix any zone pair that does not behave the way the matrix says it should | Jaden | 2026-11-05 | 2026-11-06 | 2 | 5.1 | Not started | Task
5.4 | Cross training: each member finds and fixes a fault planted in someone else's zone | All | 2026-11-06 | 2026-11-07 | 2 | 5.1 | Not started | Task
G5 | GATE Every zone pair proven; every member has fixed a fault outside their own zone | Michael | 2026-11-07 | 2026-11-07 | 1 | 5.3, 5.4 | Not started | Gate
S4 | SPRINT 4 (Jira) | All | 2026-11-10 | 2026-11-21 | 12 | G5 | Not started | Sprint
W6 | WEEK 6 Lock it down, then break it on purpose | Carl, Devam | 2026-11-10 | 2026-11-14 | 5 | G5 | Not started | Week | 2026-11-03 | 2026-11-07 | 7
6.1 | Harden device access on every router and switch so only authorized admins can log in | Devam | 2026-11-10 | 2026-11-11 | 2 | G5 | Not started | Task
6.2 | OSPF authentication on backbone links so only trusted routers share routes; user facing ports set passive | Carl | 2026-11-10 | 2026-11-11 | 2 | G5 | Not started | Task
6.3 | Cut a zone link on purpose and time how long OSPF takes to find a new path | Michael, Carl | 2026-11-12 | 2026-11-13 | 2 | 6.2 | Not started | Task
6.4 | Remove a border ACL and put it back, confirming nothing slips through in between | Jaden | 2026-11-12 | 2026-11-13 | 2 | 6.1 | Not started | Task
6.5 | After rerouting, recheck a sample of zone pairs to prove the rules still hold | Michael | 2026-11-13 | 2026-11-14 | 2 | 6.3 | Not started | Task
G6 | GATE Hardening done, every failure test run once, rules still enforced afterward | Carl | 2026-11-14 | 2026-11-14 | 1 | 6.4, 6.5 | Not started | Gate
W7 | WEEK 7 Run every test three times and write it all down | Michael, Devam | 2026-11-17 | 2026-11-21 | 5 | G6 | Not started | Week | 2026-11-10 | 2026-11-14 | 7
7.1 | Run every acceptance test; anything timed gets three runs | Michael, All | 2026-11-17 | 2026-11-19 | 3 | G6 | Not started | Task
7.2 | Record backup paths and recovery times with timestamps | Michael | 2026-11-18 | 2026-11-19 | 2 | 7.1 | Not started | Task
7.3 | Export every device config and add notes explaining any choice that is not obvious | Devam, All | 2026-11-18 | 2026-11-20 | 3 | G6 | Not started | Task
7.4 | Finish the logical and physical diagrams so they match the real build | Devam | 2026-11-19 | 2026-11-20 | 2 | 7.3 | Not started | Task
7.5 | Draft the final report and the reasoning behind each design choice | Devam, Carl | 2026-11-19 | 2026-11-21 | 3 | 7.3 | Not started | Task
G7 | GATE Every result logged with three runs each, diagrams match the build | Michael | 2026-11-21 | 2026-11-21 | 1 | 7.2, 7.4 | Not started | Gate
S5 | SPRINT 5 (Jira) | All | 2026-11-24 | 2026-12-05 | 12 | G7 | Not started | Sprint
W8 | WEEK 8 Freeze, rehearse, deliver | All | 2026-11-24 | 2026-12-01 | 8 | G7 | Not started | Week | 2026-11-17 | 2026-11-21 | 10
8.1 | Freeze the configuration and rerun the full Appendix F test plan one last time | All | 2026-11-24 | 2026-11-25 | 2 | G7 | Not started | Task
8.X | Thanksgiving, no work planned |  | 2026-11-26 | 2026-11-26 | 1 |  |  | Blackout
8.2 | Finish the report, including known limits and the root cause of any test that failed | Devam | 2026-11-27 | 2026-11-28 | 2 | 8.1 | Not started | Task
8.3 | Record the video demo with all four members narrating | All | 2026-11-27 | 2026-11-29 | 3 | 8.1 | Not started | Task
8.4 | Build the slides and rehearse the full presentation twice | All | 2026-11-29 | 2026-11-30 | 2 | 8.3 | Not started | Task
8.5 | Practice Q and A: each member answers questions on a zone they did not build | Carl | 2026-12-01 | 2026-12-01 | 1 | 8.4 | Not started | Task
G8 | GATE FINAL DELIVERY: package submitted, all four ready for any question | Carl | 2026-12-01 | 2026-12-01 | 1 | 8.2, 8.5 | Not started | Gate
BUF | Buffer: spare days between final delivery and the course deadline | All | 2026-12-02 | 2026-12-04 | 3 | G8 |  | Reserve
END | Course deadline |  | 2026-12-05 | 2026-12-05 | 1 |  |  | Deadline
MTG | Weekly team meeting: two hours minimum, all four present, run by Carl | All | 2026-09-29 | 2026-12-01 | 64 |  | Ongoing | Recurring
How to read this
Jira sprint window
Scope week, current forecast
Scope week, original baseline (where it was supposed to be)
Task
Task complete
Gate: the team does not move on until it passes
Buffer
Blackout
Course deadline
Today
PM notes
Why Week 2 moved. Thompson's design review was planned for Oct 10. He acknowledged the scope on Oct 8, which left no time to review a design that same week. The plan and matrix go to him Oct 15, the review is targeted for Oct 17, and the build weeks after it move back one week.
Why we did not cram to catch up. The scope says a missed gate means the PM replans instead of rushing. Every later week keeps its full five days. The lost week comes out of the buffer before the course deadline, which drops from two weeks to three days.
How Week 3 still started on time. While the review is pending, the team places and cables every device and writes each config as a text file. Nothing is loaded onto a device until Thompson approves, so the gate holds and no time is wasted.
Backup plan if we need more room. Start the Week 7 paperwork (config export, diagrams) during Week 6 testing, since those do not depend on the test results.
Thanksgiving lands in Week 8, so the report and video start the day after and practice Q and A moves to Dec 1.
Why this order. If ACL rules go on top of broken routing, there is no way to tell which one caused a problem. So routing is proven first, then the rules, then hardening.
Every bar, duration and slip number is calculated from the dates. Change a date and the chart redraws itself.

## Sprint Stories
What each week delivers and who it is for
Jira sprint | Scope week | Window | User story | Done when (gate) | Owner
1 | 1 | Sep 29 to Oct 3 | As the sponsor, I want the team working from one topology and one naming scheme so every config and diagram reads the same. | Topology and naming agreed, all four committing | Carl
1 into 2 | 2 | Oct 6 to Oct 17 | As the network engineer, I want an addressing plan that summarizes cleanly at each area border so routing tables stay small and readable. | Sponsor approves plan and policy matrix | Jaden
2 | 3 | Oct 20 to Oct 24 | As a user in any zone, I need to reach the rest of my own zone before anyone starts restricting traffic between zones. | Adjacencies FULL, intra zone reachability proven | Carl
3 | 4 | Oct 27 to Oct 31 | As the security officer, I want contractors and guests kept out of every internal resource while each department keeps the access it actually needs. | Every rule behaves as written, hit counters prove it | Jaden
3 | 5 | Nov 3 to Nov 7 | As an auditor, I want proof for every zone pair in both directions, not just the easy ones. | Full matrix evidenced, cross training done | Michael
4 | 6 | Nov 10 to Nov 14 | As the operations lead, I need the policy to hold after a link fails and OSPF reconverges, and I need routing updates authenticated. | Hardening applied, every failure scenario passed | Devam, Carl
4 | 7 | Nov 17 to Nov 21 | As the professor, I want repeatable results: three timed runs, exported configs and diagrams that match the build. | Matrices complete, diagrams synchronized | Michael, Devam
5 | 8 | Nov 24 to Dec 1 | As the audience, I want any one of the four presenters to explain any zone, not just their own. | Package submitted, team rehearsed twice | All

## Team Load
Roles, zone ownership and effort (Appendix C of the signed scope)
Member | Role | Owns | Tasks assigned | Hrs per week | Weeks | Planned hours
Carl Edouard | Project Manager and backbone owner | Management zone, OSPFv2 backbone and its authentication, sponsor relationship, gate checklist | 21 | 12 | 8 | 96
Jaden Torres | Zone policy and addressing lead | Engineering zone, VLSM plan, directional policy matrix, ACL design for every boundary | 18 | 12 | 8 | 96
Michael Pietrewicz | Verification and testing lead | Corporate and Contractor/Guest zones, verification and failure test matrices, evidence archive | 18 | 12 | 8 | 96
Devam Patel | Security, documentation and diagram lead | Server/DMZ zone and its service, device hardening, both diagrams, final report, exported configs | 18 | 12 | 8 | 96
Team total | [5 empty] | 384
Hours follow the signed scope: 4 members, 12 hours a week, 8 weeks.
Tasks assigned counts every task that names the member, including tasks owned by All.
Everyone configures devices and must be able to explain any zone at the final presentation. Ownership means accountability, not exclusive access.